## GANTT
QuEst (Quantifying Estrogens)
| Start Date | End Date | Start on Day | Duration | Timeline | Status
Order Chemicals | 2019-08-01 | 2019-08-08 | 0 | 7 |  | Complete
Order Tablets/Injectables | 2019-08-01 | 2019-08-15 | 0 | 14 |  | Upcoming
Review Current work with Prof. Chidsey | 2019-08-01 | 2019-08-06 | 0 | 5 |  | Complete
Develop GeneralGC/MS Procedure | 2019-08-20 | 2019-09-03 | 19 | 14 |  | Upcoming
Investigate UV/Vis Quantification Further | 2019-08-27 | 2019-09-10 | 26 | 14 |  | Upcoming
Quantify Tablets/Injectables with UV/Vis or GC/MS | 2019-09-10 | 2019-09-30 | 40 | 20 |  | Upcoming
Data Analysis / Review Work with Prof. Chidsey | 2019-09-30 | 2019-10-14 | 60 | 14 |  | Upcoming
Compare Data to Prescription Estrogen Data | 2019-10-14 | 2019-10-28 | 74 | 14 |  | Upcoming
*Note: the status may be altered as "Complete", "Active", or "Upcoming"
*Note: The colors change depending upon the timeline of the project. If a task is completed, the bar turns grey, if it is active, then it will be yellow, and if it is upcoming then it will be green.
If, however a task is active but behind schedule then it turns red. If a task is behind schedule and it is the current week then the bar turns dark red

## Budget
Item | Milestone | Cost | Link 1 | Link 2 | Notes
17β-Estradiol Reference Solution | 1 | 105 | https://www.sigmaaldrich.com/catalog/product/cerillian/e060?lang=en&region=US |  | in solution
Estradiol valerate Reference Standard | 1 | 183 | https://www.sigmaaldrich.com/catalog/product/sial/y0000046?lang=en&region=US |  | 120mg
Acetonitrile OmniSolv® LC-MS | 1 | 396 | https://www.sigmaaldrich.com/catalog/product/mm/ax0156?lang=en&region=US |  | lcms grade important for uv absorbtion
Mini-UniPrep Syringeless Filters | 1 | 512.28 | https://www.thomassci.com/Laboratory-Supplies/Syringeless-Filters/_/97EEE5C4-699E-4BA3-AF88-B91B79BEC901?q=Vial%20Septum |  | need 0.2um filters
Tablets/injectables (sorted by vendor, buying two packages each) | All estradiol/estradiol valerate
All Day Chemist | 2 | 23.48 | https://www.alldaychemist.com/progynova-2mg-tablet.html |  |  | Per Package
| 2 | 0 | https://www.alldaychemist.com/progynon-depot.html |  | (price pending on stock) | 11.74
Thialand Pharmacy | 2 | 52 | https://www.thailandpharmacy.net/product/progynova-2-mg-28-tablets/
In House Pharmacy | 1 | 104 | https://www.inhousepharmacy.vu/p-1120-progynova-2mg-3x28s.aspx |  |  | 26
| 1* | 0 | https://www.inhousepharmacy.vu/p-1162-estradiol-valerate-injection-100mg5ml.aspx |  | (price pending on stock) | 52
United Pharmacies | 2 | 63.56 | https://www.unitedpharmacies.md/Progynova-Estradiol-Valerate.html
Shape-Shifters | 2 | 4 | https://shape-shifters-eu.netlify.com/details |  |  | 31.78
Buy Online Ventolin | 2 | 38 | https://buyonlineventolin.co.uk/estrofem-estradiol-2-mg-28-film-coated-tablets-produced-by-novo-nordisk-denmark.html |  |  | 2
Shes a Lady | 2 | 22 | https://www.shesalady.co.uk/product-page/progynova-2mg-estradiol-valerate |  |  | 19
Fab Skin House | 2 | 65.7 | http://www.fabskinhouse.com/en/product/50/progynova-2mg-1-box-contains-3-packs-free-shipping-buy-5-get-1-pack-free |  |  | 11
InHomeHealthServices | 2 | 95.5 | https://inhome-health.com/product/progynova-estradiol-valerate-84-tabs-x-2mg/ |  |  | 32.85
| 2 | 73 | https://inhome-health.com/product/progynova-estradiol-valerate-84-tabs-x-2mg-bayer-zydus/ |  |  | 47.75
Pharma Online | 2 | 74 | https://pharmaonline.tv/en/product_info.php?info=p94_progynova-1-mg.html |  |  | 36.5
Beauty Store Front | 2 | 64 | https://www.beautystorefront.net/product-page/progynova-2mg-84-tablets |  |  | 37
| 1* | 130 | https://www.beautystorefront.net/product-page/progynon-depot |  |  | 32
65
Unforseen Expenses |  | 700
Shipping / Ordering |  | 200 | (can't predict well until ordering, as many require money orders / faxing which increase the price)
2905.52
*: Either or, one currently out of stock